## General
ID | General
1 | Notifications need to be stored in a sepparate file (Notifications.xlsx). It should contain 5 columns: NotificationID, NotificationTo, NotificationCC, NotificationSubject, NotificationBody. The notifications can have placeholders for the Subject or the Body, which need to be provided as an array of values in the arguments section: in_SubjectValues and in_BodyValues. Attachments can be also defined, which will be passed an an array containing the file paths and will be dinamycally attached to the email.
2 | The Auxis.Misc activity needs to be installed. Each reference to WriteToLog needs to be made using the activity, not the workflow.
3 | Resolution to be used for development and the robot is 1920x1080.
4 | When a notification needs to be sent, it needs to be sent using the SendNotification activity, for which a data table with the notifications and the ID of the notification need to be provided.
5 | Capture the time at which the robot started and ended its execution, it will be added to the final email once it completes running along with the TransactionData table, which needs to be saved as Results_YYYYMMDD_HHMMSS.xlsx and attached to the email. Use the SendResults activity for this purpose. The results file can be saved in the \Data folder.
6 | If any unexpected error is detected while executing, send an email attaching a screenshot and mark the transaction as failed (throw an ApplicationException).
7 | Use a flag to detect System Exceptions during Initizalization, Processing or End of the project. If this flag is marked as true (meaning an exception was detected), then throw an exception at the end of the execution to mark the process as failed in Orchestrator.
8 | All the process values need to be stored in Orchestrator, the config file should be used to map the assets with the values inside the code. The names of the assets in Orchestrator can't be harcoded in the project.
9 | The TransactionData should contain 4 additional columns: Status, StartTime, EndTime and ErrorMessage. The StartTime needs to be populated when each transaction starts while the Status and EndTime need to be populated once the transaction completes; the ErrorMessage is only populated if an exception is detected.
11 | The name of the project should be Amerant-PasswordReset and it has to be developed using the Auxis ReFramework.
12 | Reuse the existing library for the Service Now activities, created for the PTO project.
13 | A list with possible passwords for AS400 will be created, with at least 50 options and the robot will choose one of them randomly when doing a password reset. They will have a number at the end that will be randomly added when creating the password, between 0 and 9. The guidelines for the AS400 passwords are: - Between 8 and 10 characters - One number, anywhere in the text - Uppercase - Do not use any of the previous 10 passwords (AS400 indicates at the bottom if you're using one of the previous passwords)
14 | Important: the password should not be stored anywhere. As soon as it is generated and tested in AS400, it needs to be sent in an email. It can't be tracked in the logs or stored in the Transaction Data.

## Project Estimates
Development effort (hrs) | 3
Project size | Simple
Task | Owner | Time (hrs)
4. Solution Design |  | 19
4.02. Review PDD with developer and Support Team | Business Analyst | 1
4.03. Review DSD with developer and Support Team | Solutions Architect | 2
4.06. Process walkthrough | Developer | 12
4.07. Define project estimates | Developer | 1.5
4.08. Review estimates with the Solutions Architect | Developer | 1
4.09. Review estimates with the SCRUM Master | Developer | 1
4.13. Information uploaded to MS Teams | Developer | 0.5
5. Build RPA Solution (1st pass) |  | 3.45
5.01. All relevant ards in Monday.com are complete | Developer | 3
5.03. End-to-end testing is complete | Developer | 0.3
5.06. Code review is complete | Developer | 0.15
6. UAT (1st pass) |  | 4.8
6.03. All test cases were completed | Developer | 0.3
6.04. Test results tracked | Developer | 2
6.06. Process execution time was benchmarked | Developer | 2
6.09. Information uploaded to MS Teams | Developer | 0.5
5. Build RPA Solution (2nd pass) |  | 17.78
5.01. All relevant ards in Monday.com are complete | Developer | 0.6
5.02. Latest code pushed to GitHub | Developer | 0.5
5.03. End-to-end testing is complete | Developer | 0.12
5.06. Code review is complete | Developer | 0.06
5.07. SDD is up-to-date | Developer | 8
5.09. Exception SOPs were created | Developer | 8
5.10. Information uploaded to MS Teams | Developer | 0.5
6. UAT (2nd pass) |  | 6.8
6.03. All test cases were completed | Developer | 0.3
6.04. Test results tracked | Developer | 2
6.06. Process execution time was benchmarked | Developer | 2
6.08. Robot execution video | Developer | 2
6.09. Information uploaded to MS Teams | Developer | 0.5
7. Go Live |  | 9.5
7.03. Deployment guide was completed | Developer | 4
7.04. Accounts stored in PMP | Infrastructure Team | 1
7.06. Assets and queues created in Orchestrator | Developer | 2
7.07. Packages and libraries uploaded to Orchestrator | Developer | 1
7.08. Triggers created in Orchestrator | Developer | 1
7.12. Information uploaded to MS Teams | Developer | 0.5
8. Transition to support |  | 6.8
8.01. Validate process is stable | Developer | 0.3
8.02. Transition session coordinated with Support Team | Developer | 0.5
8.06. Code walkthrough | Developer | 4
8.07. Exception SOPs review | Developer | 2
Meetings |  | 6.1
Total |  | 74.23

## TransactionData
TaskNumber | Application | Username | UserEmail | Status | StartTime | EndTime | ErrorMessage
AS400 for now

## Workflows
System | Name | Purpose | Input | Output | Comments | Effort SA | Technology | Complexity | Development | Testing | Effort Dev | Revised Effort
Misc | Test | Test | in_NotificationsFile | out_dt_Notifications | Load the notifcations | 3 | Business logic (no app.) |  |  |  |  | 3
[5 empty] | Development | 3 | [5 empty] | 3

## Reference (hidden)
Task | Owner | Simple | Low | Medium | High | Highlights | Complexity
4. Solution Design |  | 6 | 9 | 16 | 24 |  | Complexity | Development | Unit Testing | Total effort
4.02. Review PDD with developer and Support Team | Business Analyst | 1 | 2 | 4 | 6 |  | Very simple (<=5 steps) | 2 | 0.5 | 2.5
4.03. Review DSD with developer and Support Team | Solutions Architect | 1 | 1 | 1.5 | 2 |  | Simple (6-10 steps) | 4 | 1 | 5
4.06. Process walkthrough | Developer | 2 | 4 | 8 | 12 |  | Medium (11-15 steps) | 6 | 1.5 | 7.5
4.07. Define project estimates | Developer | 0.5 | 0.5 | 1 | 1.5 |  | High (16-20 steps) | 8 | 2 | 10
4.08. Review estimates with the Solutions Architect | Developer | 0.5 | 0.5 | 0.5 | 1 |  | Very high (21-25 steps) | 12 | 3 | 15
4.09. Review estimates with the SCRUM Master | Developer | 0.5 | 0.5 | 0.5 | 1 |  | Extremely complex (> 25 steps) | 16 | 4 | 20
4.13. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5 |  | Reused | 1 | 0.5 | 1.5
5. Build RPA Solution (1st pass) |  | 50.6 | 116.15 | 194.35 | 319.7
5.01. All relevant ards in Monday.com are complete | Developer | 44 | 101 | 169 | 278 | Includes coding, unit testing and integration testing
5.03. End-to-end testing is complete | Developer | 4.4 | 10.1 | 16.9 | 27.8 | 10% of the original development time | Multipliers
5.06. Code review is complete | Developer | 2.2 | 5.05 | 8.45 | 13.9 | 5% of the original development time | Type | Multiplier
6. UAT (1st pass) |  | 5.9 | 11.6 | 19.4 | 32.3 |  | Business logic (no app.) | 0.75
6.03. All test cases were completed | Developer | 4.4 | 10.1 | 16.9 | 27.8 | 10% of the original development time | Standard app. | 1
6.04. Test results tracked | Developer | 0.5 | 0.5 | 1 | 2 |  | Complex app. | 1.25
6.06. Process execution time was benchmarked | Developer | 0.5 | 0.5 | 1 | 2 |  | Java | 1.25
6.09. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5 |  | Citrix\RDP | 1.5
5. Build RPA Solution (2nd pass) |  | 20.44 | 35.26 | 56.94 | 89.28 |  | Terminal\Console | 1.5
5.01. All relevant ards in Monday.com are complete | Developer | 8.8 | 20.2 | 33.8 | 55.6 | 20% of the original development time | Image recognition | 1.5
5.02. Latest code pushed to GitHub | Developer | 0.5 | 0.5 | 0.5 | 0.5
5.03. End-to-end testing is complete | Developer | 1.76 | 4.04 | 6.76 | 11.12 | 20% of the 2nd. development time
5.06. Code review is complete | Developer | 0.88 | 2.02 | 3.38 | 5.56 | 10% of the 2nd. development time
5.07. SDD is up-to-date | Developer | 4 | 4 | 6 | 8
5.09. Exception SOPs were created | Developer | 4 | 4 | 6 | 8
5.10. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5
6. UAT (2nd pass) |  | 6.9 | 12.6 | 21.4 | 34.3
6.03. All test cases were completed | Developer | 4.4 | 10.1 | 16.9 | 27.8 | 10% of the original development time
6.04. Test results tracked | Developer | 0.5 | 0.5 | 1 | 2
6.06. Process execution time was benchmarked | Developer | 0.5 | 0.5 | 1 | 2
6.08. Robot execution video | Developer | 1 | 1 | 2 | 2
6.09. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5
7. Go Live |  | 5 | 5.5 | 9.5 | 9.5
7.03. Deployment guide was completed | Developer | 2 | 2 | 4 | 4
7.04. Accounts stored in PMP | Infrastructure Team | 0.5 | 1 | 1 | 1
7.06. Assets and queues created in Orchestrator | Developer | 1 | 1 | 2 | 2
7.07. Packages and libraries uploaded to Orchestrator | Developer | 0.5 | 0.5 | 1 | 1
7.08. Triggers created in Orchestrator | Developer | 0.5 | 0.5 | 1 | 1
7.12. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5
8. Transition to support |  | 6.9 | 13.6 | 22.4 | 34.3
8.01. Validate process is stable | Developer | 4.4 | 10.1 | 16.9 | 27.8 | 10% of the original development time
8.02. Transition session coordinated with Support Team | Developer | 0.5 | 0.5 | 0.5 | 0.5
8.06. Code walkthrough | Developer | 1 | 2 | 3 | 4
8.07. Exception SOPs review | Developer | 1 | 1 | 2 | 2
Meetings |  | 9 | 18 | 30 | 48 | 3 hours per week
Total |  | 110.74 | 221.71 | 369.99 | 591.38

## Assets
Name | Content
PR_AS400_PasswordsFile | File containing the possible passwords to use when resetting an accoun in AS400.
PR_ServiceNow_Credential | Credential to use to connect to ServiceNow.
PR_ServiceNow_URL | URL for ServiceNow.
PR_ServiceNow_Secret | Secret and API keys for the ServiceNow API.
PR_ServiceNow_Queue | Queue from where to pull the requests from ServiceNow.
PR_ServiceNow_ReassignmentQueue | Queue to which the tasks are assigned in case an error is detected.

## Notifications
NotificationID | NotificationTo | NotificationCC | NotificationSubject | NotificationBody
LoginError | RPASupport@auxis.com |  | {Process} - {0} login error | Hi,<br /> <br /> The RPA process encountered an error when trying to login to {0}. Please validate if the webpage is working and the credentials.<br /> <br /> <br /> Thank you
UnexpectedError | RPASupport@auxis.com |  | {Process} - Unexpected error | Hi,<br /> <br /> An unexpected error ocurred while processing.<br /> <b>Activity:</b> {0}.<br /> <b>Error message:</b> {1}.<br /> <br /> <br /> Thank you
EndProcess | RPAResults@auxis.com |  | {Process} - Process completed | Hi,<br /> <br /> The process completed executing. Attached you can find the results.<br /> <br /> <br /> Thank you
EndProcessNoData | RPAResults@auxis.com |  | {Process} - Process completed - No data | Hi,<br /> <br /> The process completed executing but there were no transactions.<br /> <br /> <br /> Thank you